## Slide 1: MINISTRY OF REGIONAL DEVELOPMENT AND PUBLIC WORKS DG “PROGRAMMING OF THE REGIONAL DEVELOPMENT” OPERATIONAL PROGRAMME “REGIONAL DEVELOPMENT” 2007-2013 EVALUATION PLAN

## Slide 2: Necessity and importance of the OPRD Evaluation plan
Evaluation is a key component in the processes of programming and implementing Structural and Cohesion funds.
The general aim of evaluation in the context of Structural funds is “to improve the quality, effectiveness and consistency of the assistance from the Funds and the strategy and implementation of operational programmes with respect to the specific structural problems affecting the Member State and regions concerned…” (Art. 47 §1 GR 1083/2006)
  The effects of evaluation could be expressed in:
  Improving allocation of recourses;
  Improving programme implementation by identifying what works and what does not work, and
  Ensuring the necessary accountability before taxpayers, incl. by demonstration of the impacts of interventions.

## Slide 3: Nature and aim of OPRD Evaluation plan
The evaluation plan is a way to structure the activities for carrying out on-going evaluation. It creates an appropriate tool for timely identification and initiation of the necessary and sufficient evaluations and for ensuring their implementation and use.
OPRD evaluation plan has been elaborated on the basis of need analysis and implementation of the requirements and recommendations of Regulation 1083/2006 and Working Document № 5 of European Commission
The aim of the evaluation plan is to create a general frame for on-going evaluation and to ensure its effective use and integration as a management tool during the period of OPRD implementation.

## Slide 4: Envisaged activities in the Evaluation plan /1/
The Evaluation plan envisages several types of activities, namely:
1) Obligatory evaluations, required on revealing significant departure from the goals initially set and on proposals for significant changes in the Operational programme /Art 48 (3) of Regulation 1083/2006)
2) Specific evaluations, defined on the basis of identified needs during plan preparation related to the management of operational programme

## Slide 5: Envisaged activities in the Evaluation plan /2/
3) Supporting activities, ensuring conditions for effective implementation of the evaluations – elaboration of methods, standards, researches for collecting information etc.
4) Providing connection with the monitoring system as an important tool for initiation of evaluations and basic source for their informational supply.
5) Activities for dissemination and use of evaluation results as well as for recurrent review and updating of the evaluation plan

## Slide 6: Indicative list , time-table and financial recourses
Planned activities for on-going evaluation present:
0,2 % of the total financial recourses of OPRD
6,2 % of the financial recourses of Priority axis 5 “Technical assistance”

## Slide 9: Obligations and responsibilities for carrying out evaluations
The implementation of OPRD Evaluation plan is realized by a system of management, which includes:
OPRD Managing Authority responsible for ensuring the entire organization, coordination and implementation of the Evaluation plan in accordance with the principles and decrees of SF and Bulgarian legislation
Steering Group for evaluation of OPRD, which general function is to support the coordination and sharing information on the issues relevant to OPRD evaluation
Monitoring Committee of OPRD, responsible for making periodical review on the evaluation results and the implementation of recommendations.

## Slide 10: Approval, review and updating of OPRD evaluation plan
- The plan for on-going evaluation of OPRD is approved by the Head of Managing Authority at the proposal of the Head of Evaluation Unit after coordination with the concerned units in the MA
After the approval the plan for on-going evaluation is presented before the Monitoring Committee for notices and comments.
Regular review of the evaluation plan is carried out by the Steering Group for OPRD Evaluation once a year before the spring session of the Monitoring Committee.
Changes of the evaluation plan are approved by the Head of Managing Authority and are presented at sessions of the Monitoring Committee.
The review of the evaluation plan also includes preparation of an annual report for the implementation of the evaluation plan which is also presented to the Monitoring Committee.

## Slide 11: Independence of evaluation
In conformity with the principle of independency grounded in § 47 [3] of the Regulation No 1083/2006, the planned evaluations will be carried out by experts or bodies, that are functionally independent of the certifying and auditing authorities.
In the majority of the cases, according to the internationally accepted standards, the evaluators will be independent also from the MA of OPRD.
It is envisaged that the prevailing part of OPRD evaluations will be carried out by internal evaluators, selected according to the Law of public procurements on the base of clearly defined criteria which guarantee high quality and professionalism.

## Slide 12: Use and dissemination of evaluation results
The main /potential/ users of information about the OPRD on-going evaluations are:
- Managing Authority of OPRD
- Monitoring Committee of OPRD
- Central Unit for Coordination and the Managing authorities of other operational programs
- European Commission
- Independent evaluators
- OPRD beneficiaries /especially in terms of dissemination and use of evaluation results/.

## Slide 13: Disseminating final results, conclusions and recommendations of evaluations
Overall reports of evaluations are submitted to the interested, for example departments in MA and members of MC.
Summary of reports in Bulgarian and English is published on the official website of the Operational Programme
Conferences, discussions, seminars/workshops will be carried out in case of need for a wider discussion of the results and recommendations of evaluations
Other information materials /brochures, bulletins, press-releases etc/ will be prepared if there is need for wider dissemination
Annual review of the evaluations carried out, their basic results and recommendations will be published /entirely or in summary/ on the official website of OPRD
Main results of the evaluations are included in the annual report for OPRD implementation according to Art. 67 of Regulation 1083/2006

## Slide 14
Thank you for your attention!
DG “PROGRAMMING OF REGIONAL DEVELOPMENT”
WWW.BGREGIO.EU